## Sheet1
Function / Milestone |  |  |  | Prabha off | FTB9050-80-150 delivery | [10 empty] | A-sample BMS | [5 empty] | A-sample Module
Week nr | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Functions SW
Soc (LFP) | Impl. | [8 empty] | Verif. | Verif.
Current limits |  | Impl. | Impl. | Impl. | [7 empty] | Verif. | Verif.
Sop
Contactor control | [6 empty] | Verif.
Cell balancing |  |  | Impl. | Impl. | Impl.
Cycle counter | [8 empty] | Verif.
Limit violation | [7 empty] | Verif.
Signal pre-processing |  | Impl. | Impl. |  |  |  | Verif.
Cell characterization | [7 empty] | Test. | Test. | Test. | Test. | Test.
IRM
Inverter / Tester Integration
FTB9050-80-150 |  |  |  |  | Integr. | Integr.
HW - Electrical
BMS PCB | Design | Design | Design |  |  | Verif. | Verif. | Design |  |  | Verif. | Design |  |  | Verif.
CMU PCB |  |  | Design |  | Design | Design |  |  | Verif. | Design |  |  | Verif. | Design |  |  | Verif.
BDU PCB
Module adapter PCB 12c | [6 empty] | Design | Design |  |  | Verif. | Design |  |  | Verif.
HW - Mechanical
Module casing 12c | Design |  |  | Verif.
Wiring / harness install. | Design |  |  | Verif.
Rack
Note on A22: faouzi_al@hotmail.com: No need for PCB in a-sample
Note on A23: faouzi_al@hotmail.com: Specific for CALB L135F72
Note on A26: faouzi_al@hotmail.com: Specific for CALB L135F72
Note on A27: faouzi_al@hotmail.com: this lays purely on purchasing. This includes: Busbar Amphenol connectors Crimping tool Riveting tool Rivets HV cables HV Contactors